Deepfake Detection and Media Verification System

Team Plan: Work Division, Final Tech Stack and Repository Structure

Team: Manish, Sidhhesh, Vedant   |   Build window: 1 week (MVP)   |   October 2026

# 1. Project Overview

The system checks whether an uploaded image, video or audio file is authentic, manipulated or AI-generated. Several independent modules analyse the file, their results are fused into one suspicious score with a label (Likely Authentic, Suspicious or Likely Fake), and the user can download a PDF verification report showing the evidence.

## 1.1 One-week MVP scope

A full build with fine-tuned models does not fit in one week with three people, so the plan is an end-to-end working demo using pretrained models. Training can follow as a second phase.

| Original plan | One-week version |
| --- | --- |
| Fine-tune EfficientNet and Wav2Vec2 | Use pretrained Hugging Face detectors, no training |
| FaceForensics++ and Celeb-DF datasets | Skip (access requests take days). Test on a small real/fake set the team collects |
| Blink, lip-sync and LSTM temporal checks | Dropped. Video = sampled frames + image model + simple flicker check |
| Celery and Redis | Python threading / concurrent.futures |
| Fusion by logistic regression | Weighted average |
| PostgreSQL | SQLite |
| Grad-CAM explanations | ELA heatmaps only |

Still in scope: upload for all three file types, image/video/audio verdicts, metadata and OCR, fused score and label, PDF report, SHA-256 result caching and a basic dashboard.

# 2. Team Roles and Work Division

Work is divided along module boundaries. Each person owns their own folders, so nobody edits the same files and merge conflicts stay rare.

| Member | Role | Owns |
| --- | --- | --- |
| Manish | Backend, integration, fusion and report lead | Flask app, database, upload validation, hash cache, file-type routing, background jobs, score fusion, PDF report, Docker, deployment, README |
| Sidhhesh | Image and video ML lead | Face detection, pretrained image classifier(s), ELA and noise heatmap, video frame sampling and aggregation, flicker check, image/video evaluation |
| Vedant | Audio, metadata/OCR and frontend lead | Audio preprocessing and classifier, exiftool/EXIF rules, OCR, upload page, results dashboard, progress bar, mobile layout, audio evaluation |

## 2.1 Manish: Backend, integration, fusion and report

- Flask app factory, blueprints, configuration and SQLAlchemy models (User, Submission, Result, Report).

- Upload route: validate type and size, sanitise filename, compute SHA-256, return the stored result when the hash already exists.

- Pipeline service: detect file type, run the matching modules from the registry, collect their results.

- Background job executor with a status endpoint so the UI can show progress for video and audio.

- Fusion: weighted score (ML 50%, forensics 25%, metadata 15%, audio 10%, reweighted when a module is missing) and label thresholds; confidence reduced when modules disagree.

- PDF report with ReportLab: scores, evidence, heatmaps, metadata table, limitations.

- Delete uploads after analysis, Dockerfile, deployment to Hugging Face Spaces, README and LICENSES.md.

## 2.2 Sidhhesh: Image and video ML

- Face detection with MTCNN or MediaPipe; fallback to a whole-image classifier when no face is found.

- Pick, test and compare pretrained image deepfake / AI-image detectors; keep the best (ideally two, averaged).

- ELA and noise-residual heatmap returned as an image path for the dashboard and report.

- Video module: sample about 1 frame per second (capped at about 30 frames and 30 seconds), score each frame with the image model, aggregate with mean and max, add a frame-to-frame flicker check.

- Run each model on the team test set and record accuracy in eval/results.md.

## 2.3 Vedant: Audio, metadata/OCR and frontend

- Audio preprocessing with librosa/ffmpeg: 16 kHz mono, 4-second clips, average clip scores; pretrained Wav2Vec2-based spoof detector.

- Metadata module: exiftool and Pillow EXIF rules (missing camera data, editing-software tags, timestamp conflicts).

- OCR module with Tesseract or EasyOCR on images and video frames.

- Frontend: upload page, results dashboard (scores, heatmap, flagged frames, metadata table), job progress bar, limitation messages, mobile-friendly layout.

- Collect the audio part of the test set and record accuracy.

## 2.4 Shared responsibilities

- Agree the module interface (modules/base.py) together in the first hour, then freeze it.

- Build the team test set on Day 1: about 30 real + 30 fake images, 10 + 10 audio clips, 5 + 5 short videos.

- Keep LICENSES.md up to date: add a row the moment a model or dataset is added.

- Write tests for the interface contract; contribute screenshots and failure cases for the limitations section.

# 3. One-Week Schedule

Rule for Day 1: integration comes first. By the end of the day every module must return fake scores through the real pipeline, so later days only replace stubs with real models.

| Day | Manish | Sidhhesh | Vedant |
| --- | --- | --- | --- |
| 1 | Repo, Flask skeleton, SQLite models, upload validation, analyze() interface and stubs | Pick and test a pretrained image detector, face detection | Upload page and base template, EXIF reader |
| 2 | Hash cache, file-type routing, background job and status endpoint | ELA heatmap; image module returns {score, evidence} | Pick and test a pretrained audio detector, librosa preprocessing |
| 3 | Fusion logic and labels, results API; test deploy with one model | Video: frame sampling, per-frame scoring, mean/max aggregation | Results dashboard (scores, heatmap, metadata table), OCR |
| 4 | PDF report with ReportLab | Flicker check and no-face fallback | Audio module wired in, progress bar for jobs |
| 5 | Integration, bug fixing, delete-after-analysis | Test on 20 to 30 samples, record results | Mobile layout, error and limitation messages |
| 6 | Docker, README, LICENSES.md, full deployment test | Collect failure cases for the limitations section | Demo script and screenshots |
| 7 | Buffer, deploy to Hugging Face Spaces, rehearse demo | Buffer, fix model issues | Buffer, fix UI issues |

# 4. Final Technology Stack

Everything is open source and free. Python 3.10 or newer is required; a laptop with 8 GB RAM is enough because inference runs on CPU with small models.

## 4.1 Application stack

| Layer | Technology | Used for | Owner |
| --- | --- | --- | --- |
| Backend | Python, Flask, Flask blueprints | REST API, routing, module orchestration | Manish |
| Database | SQLite with SQLAlchemy ORM | Users, submissions, results, reports | Manish |
| Background jobs | concurrent.futures / threading | Slow video and audio analysis | Manish |
| Report | ReportLab | PDF verification report | Manish |
| Frontend | HTML, CSS, JavaScript, Bootstrap, Jinja templates | Upload page, dashboard, report download | Vedant |
| Packaging | Docker (installs ffmpeg, Tesseract, exiftool) | Reproducible runs and deployment | Manish |
| Hosting | Hugging Face Spaces (Docker Space) | Free demo hosting | Manish |
| Collaboration | Git and GitHub (PRs, CODEOWNERS) | Version control and review | All |

## 4.2 Processing and ML libraries

| Area | Libraries / tools | Owner |
| --- | --- | --- |
| Image and video processing | OpenCV, Pillow, NumPy, ffmpeg | Sidhhesh |
| Deep learning | PyTorch, torchvision, Hugging Face Transformers, timm | Sidhhesh, Vedant |
| Face detection | MTCNN (facenet-pytorch) or MediaPipe | Sidhhesh |
| Audio processing | librosa, torchaudio, ffmpeg | Vedant |
| OCR | Tesseract or EasyOCR | Vedant |
| Metadata | exiftool, Pillow EXIF | Vedant |

## 4.3 Models used in the one-week MVP

| Function | Model / technique | Source |
| --- | --- | --- |
| Face detection | MTCNN or MediaPipe Face Detection | Pretrained, open source |
| Image deepfake classification | Pretrained Hugging Face deepfake / AI-image detector (EfficientNet-B0 class); best one or two kept after testing | Hugging Face (check licence) |
| Image forensics | Error Level Analysis and noise residual heatmap | Classical image processing |
| Video | Image classifier on sampled frames (mean and max) + flicker check | Frames from the upload |
| Audio deepfake detection | Pretrained Wav2Vec2-based spoof detector on 16 kHz clips | Hugging Face (check licence) |
| Metadata analysis | Rule-based checks on EXIF/XMP | File metadata |
| Score fusion | Weighted average (logistic regression later) | Built in this project |

Phase 2 (after the MVP works): fine-tune EfficientNet-B0 on FaceForensics++ / Celeb-DF subsets and Wav2Vec2 on ASVspoof / WaveFake using free Colab or Kaggle GPUs, then swap the weights in without changing the app.

# 5. Repository Structure

One GitHub repository with a folder per module. The comment at the end of each line shows the owner.

deepfake-verification/

|-- README.md                   (Manish)

|-- LICENSES.md                 (shared: model/dataset, licence, date)

|-- requirements.txt            (pinned; changed only via PR)

|-- Dockerfile                  (Manish: ffmpeg, tesseract, exiftool)

|-- .env.example

|-- .gitignore                  (uploads/, instance/, weights/, *.db)

|-- run.py

|-- .github/

|   |-- CODEOWNERS

|   `-- pull_request_template.md

|

|-- app/                        (MANISH)

|   |-- __init__.py             Flask app factory

|   |-- config.py, extensions.py, models.py

|   |-- routes/                 upload.py, results.py, reports.py

|   |-- services/               pipeline.py, jobs.py, cleanup.py

|   `-- utils/                  files.py, hashing.py

|

|-- modules/

|   |-- base.py                 SHARED CONTRACT (frozen after hour 1)

|   |-- registry.py             file type -> detectors

|   |-- image/                  (SIDHHESH) face.py, classifier.py, ela.py

|   |-- video/                  (SIDHHESH) frames.py, temporal.py

|   |-- audio/                  (VEDANT)   preprocess.py, classifier.py

|   `-- meta_ocr/               (VEDANT)   metadata.py, ocr.py

|

|-- fusion/                     (MANISH) scoring.py, labels.py

|-- reports/                    (MANISH) pdf_report.py, assets/

|-- templates/                  (VEDANT) base.html, index.html, result.html

|-- static/                     (VEDANT) css/, js/, img/

|-- weights/                    gitignored; download_weights.py fetches from HF

|-- eval/                       (SIDHHESH + VEDANT)

|   |-- test_set/               own real/fake samples

|   |-- run_eval.py

|   `-- results.md              measured accuracy for the report

|-- tests/                      test_contract.py, test_pipeline.py, test_fusion.py

|-- notebooks/                  Colab/Kaggle training (phase 2)

|-- docs/                       architecture, interface spec, demo script

`-- instance/                   SQLite db (gitignored)

## 5.1 Shared module contract (modules/base.py)

Every detector implements the same interface so the fusion and report code never changes when a model is swapped. Freeze this on Day 1; any later change needs a PR reviewed by all three.

from dataclasses import dataclass, field

@dataclass

class ModuleResult:

module: str              # "image", "audio", ...

score: float | None      # 0-1 suspicious; None if skipped/failed

evidence: dict = field(default_factory=dict)

heatmap_path: str | None = None

error: str | None = None

class Detector:

name: str

supports: tuple[str, ...]        # ("image",), ("video",), ...

def analyze(self, path: str) -> ModuleResult: ...

## 5.2 Folder ownership

| Owner | Folders | Reviewer |
| --- | --- | --- |
| Manish | app/, fusion/, reports/, Dockerfile, requirements.txt, README.md | Sidhhesh or Vedant |
| Sidhhesh | modules/image/, modules/video/, eval/ (image, video) | Manish |
| Vedant | modules/audio/, modules/meta_ocr/, templates/, static/, eval/ (audio) | Manish |
| Shared (all review) | modules/base.py, tests/, LICENSES.md, docs/ | All three |

CODEOWNERS enforces this automatically:

/app/               @manish-username

/fusion/            @manish-username

/reports/           @manish-username

/modules/image/     @sidhhesh-username

/modules/video/     @sidhhesh-username

/modules/audio/     @vedant-username

/modules/meta_ocr/  @vedant-username

/templates/         @vedant-username

/static/            @vedant-username

/modules/base.py    @manish-username @sidhhesh-username @vedant-username

# 6. Team Workflow

## 6.1 Git rules

- main is always runnable and protected: no direct pushes, one approval per pull request.

- One branch per person per feature, for example feature/sidhhesh-ela-heatmap.

- Small, frequent commits with clear messages, for example "image: add ELA heatmap".

- Pull before starting each day and merge to main at least once a day.

- Day 1 order: Manish pushes the skeleton and stub modules first; Sidhhesh and Vedant then clone and branch from it.

- Each person edits only their own folders. Shared files (app.py, fusion, DB models) go through Manish.

## 6.2 Coordination

- 10-minute daily check-in: what is done, what is blocked, what interface changes are needed.

- End-of-day merge checkpoint: main must run the full demo. If it does not, fixing main comes first next morning.

- Pinned requirements.txt, updated only through pull requests, to avoid "works on my machine" issues.

# 7. Risks and How to Handle Them

| Risk | Mitigation |
| --- | --- |
| Pretrained models perform badly on unseen generators | Use two detectors per type and average; build your own test set on Day 1 and measure each model; drop models near 50% accuracy; make Suspicious a wide middle band (about 0.35 to 0.65); report only measured accuracy and state that new generators may fail. |
| Licence problems | Filter Hugging Face by licence (Apache-2.0, MIT); log every model and dataset in LICENSES.md; skip anything with no licence; label the demo "research use only". |
| Video too slow on CPU | Reject files over about 30 s or 50 MB; cap at about 30 frames resized to about 224 px; run as a background job with progress; cache by SHA-256; keep 2 or 3 pre-cached demo results as a fallback. |
| Hosting on Hugging Face Spaces | Test deployment on Day 3 or 4 with one model; load models once at startup; use small models; use a Docker Space for ffmpeg, Tesseract and exiftool; keep a screen recording and a local laptop demo as plan B. |
| Three people conflicting | Agree and freeze the interface in hour 1; stub modules first; own-folder rule; PRs only; daily check-in and merge checkpoint. |

## Limitations to state in the app and report

- Results are probabilities, not proof.

- Heavy compression, low resolution and noisy audio reduce accuracy.

- Detectors can fail on generation methods they were not trained on.

- Credit every model, dataset and repository used, and list licences in the README.